## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1 | Requirements Gathering |  |  | 2026-05-04 | 2026-05-08 | 5 | 100 | Completed | Alice
2 | System Design | 1 |  | 2026-05-12 | 2026-05-16 | 5 | 0 | Not Started | Bob
3 | Implementation | 2 |  | 2026-05-20 | 2026-05-29 | 10 | 0 | Not Started | Carol
4 | Testing | 3 |  | 2026-06-02 | 2026-06-06 | 5 | 0 | Not Started | Dave
5 | Deployment | 4 |  | 2026-06-10 | 2026-06-12 | 3 | 0 | Not Started | Eve

## Settings
Setting | Value
Project Name | CPM Linear Chain
Theme Name | Notion Light
Theme BG Primary | #ffffff
Theme BG Secondary | #f7f7f5
Theme BG Tertiary | #edece9
Theme BG Hover | #e8e7e4
Theme Border | #e0dfdc
Theme Border Subtle | #ebebea
Theme Text Primary | #1f1f1f
Theme Text Secondary | #6b6b6b
Theme Text Muted | #9b9b9b
Theme Accent | #2383e2
Theme Accent Hover | #1a6dbe
Theme Success | #0f7b0f
Theme Warning | #d97706
Theme Danger | #e03e3e
Theme Info | #2383e2
Theme Critical Path | #e03e3e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | false
Show Scale Buttons | true
Show Week Labels | false
Show Month Labels | true
Show Day Labels | true
Visible Columns | id,name,dependency,duration,startDate,endDate,progress,status,owner
Category Colors | {}