## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1.0 | Civil Works & Chiller Foundations |  | Summary | 2026-03-09 | 2026-03-20 | 10 | 0 | Not Started
2.0 | Structural Steel & Gantry Works | 1.0 | Summary | 2026-03-23 | 2026-05-01 | 30 | 0 | Not Started |  | 6 weeks
2.1 | Purchase Steel Material | 1.0 | Procurement | 2026-03-23 | 2026-04-03 | 10 | 0 | Not Started |  |  |  |  | 2.0
2.2 | Reuse Steel Material (Remove rust & Painting) | 1.0 | Construction | 2026-03-23 | 2026-04-03 | 10 | 0 | Not Started |  |  |  |  | 2.0
2.3 | Outdoor Gantry Works | 2.1,2.2 | Construction | 2026-04-06 | 2026-05-01 | 20 | 0 | Not Started |  |  |  |  | 2.0
2.4 | Indoor Gantry Works | 2.1,2.2 | Construction | 2026-04-06 | 2026-05-01 | 20 | 0 | Not Started |  |  |  |  | 2.0
2.5 | POD Gantry Works | 2.1,2.2 | Construction | 2026-04-06 | 2026-04-17 | 10 | 0 | Not Started |  |  |  |  | 2.0
3.0 | POD Ceiling, Wall & Floor (Renovation) | 2.0 | Summary | 2026-04-20 | 2026-05-22 | 25 | 0 | Not Started |  | 5 weeks
3.1 | ESD Tile | 3.0 | Construction | 2026-04-27 | 2026-05-08 | 10 | 0 | Not Started |  |  |  |  | 3.0
3.2 | Wall Frame (South & East side) | 3.0 | Construction | 2026-04-20 | 2026-05-01 | 10 | 0 | Not Started |  |  |  |  | 3.0
3.3 | Partition Walls (South side & East side) | 3.2 | Construction | 2026-05-04 | 2026-05-15 | 10 | 0 | Not Started |  |  |  |  | 3.0
3.4 | Wall Frame (North side) | 3.0 | Construction | 2026-04-20 | 2026-05-01 | 10 | 0 | Not Started |  |  |  |  | 3.0
3.5 | Partition Walls (North side) | 3.4 | Construction | 2026-05-04 | 2026-05-15 | 10 | 0 | Not Started |  |  |  |  | 3.0
3.6 | Ceiling (incl. Lighting) | 3.2,3.4 | Construction | 2026-05-04 | 2026-05-22 | 15 | 0 | Not Started |  |  |  |  | 3.0
4.0 | Equipment Installation (Chiller & CW305) | 1.0 | Summary | 2026-04-06 | 2026-05-08 | 25 | 0 | Not Started |  | 5 weeks
4.1 | Chiller Installation | 1.0 | Installation | 2026-04-06 | 2026-04-24 | 15 | 0 | Not Started |  |  |  |  | 4.0
4.2 | CW305 Installation | 1.0 | Installation | 2026-04-06 | 2026-04-24 | 15 | 0 | Not Started |  |  |  |  | 4.0
4.3 | Pumps Installation | 4.1,4.2 | Installation | 2026-04-27 | 2026-05-08 | 10 | 0 | Not Started |  |  |  |  | 4.0
4.4 | Fence Installation | 4.1,4.2 | Installation | 2026-04-27 | 2026-05-01 | 5 | 0 | Not Started |  |  |  |  | 4.0
5.0 | MEP - Chilled Water Piping Installation | 4.0 | Summary | 2026-04-13 | 2026-05-08 | 20 | 0 | Not Started |  | 4 weeks
5.1 | Piping | 4.1 | MEP | 2026-04-13 | 2026-04-24 | 10 | 0 | Not Started |  |  |  |  | 5.0
5.2 | Pneumatic testing | 5.1 | MEP | 2026-04-27 | 2026-05-01 | 5 | 0 | Not Started |  |  |  |  | 5.0
5.3 | Pipe Flushing | 5.2 | MEP | 2026-05-04 | 2026-05-08 | 5 | 0 | Not Started |  |  |  |  | 5.0
5.4 | Pipe Insulation | 5.1 | MEP | 2026-04-27 | 2026-05-08 | 10 | 0 | Not Started |  |  |  |  | 5.0
6.0 | MEP - Electrical Power Installation | 1.0 | Summary | 2026-04-13 | 2026-05-01 | 15 | 0 | Not Started |  | 3 weeks
6.1 | Switch Panel | 1.0 | MEP | 2026-04-13 | 2026-04-24 | 10 | 0 | Not Started |  |  |  |  | 6.0
6.2 | Cable Tray Installation | 6.1 | MEP | 2026-04-20 | 2026-05-01 | 10 | 0 | Not Started |  |  |  |  | 6.0
6.3 | Cabling and Termination | 6.1 | MEP | 2026-04-27 | 2026-05-08 | 10 | 0 | Not Started |  |  |  |  | 6.0
7.0 | Fire Protection System Installation | 1.0 | Summary | 2026-03-30 | 2026-05-08 | 30 | 0 | Not Started |  | 6 weeks
7.1 | Design and Permit | 1.0 | Planning | 2026-03-30 | 2026-04-17 | 15 | 0 | Not Started |  |  |  |  | 7.0
7.2 | System Installation | 7.1 | Installation | 2026-04-20 | 2026-05-08 | 15 | 0 | Not Started |  |  |  |  | 7.0
8.0 | Inspection, Testing & Cleaning | 3.0,4.0,5.0,6.0,7.0 | QA | 2026-05-11 | 2026-05-15 | 5 | 0 | Not Started
9.0 | Commissioning and Hang over | 8.0 | Delivery | 2026-05-18 | 2026-05-22 | 5 | 0 | Not Started

## Settings
Setting | Value
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | true
Visible Columns | id,name,category,duration,startDate,endDate,status,remarks