## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1 | Project Kickoff |  | Planning | 2026-05-04 | 2026-05-08 | 5 | 100 | Completed | Alice | Initial planning and alignment
2 | Requirements Gathering | 1 | Planning | 2026-05-11 | 2026-05-22 | 10 | 80 | In Progress | Bob | Stakeholder interviews
3 | System Design | 2 | Design | 2026-05-25 | 2026-06-05 | 10 | 0 | Not Started | Carol | Architecture documentation
4 | Backend Development | 3 | Development | 2026-06-08 | 2026-07-03 | 20 | 0 | Not Started | Dave | API and database layer
5 | Frontend Development | 4 | Development | 2026-07-06 | 2026-07-24 | 15 | 0 | Not Started | Eve | UI implementation
6 | Testing | 5 | QA | 2026-07-27 | 2026-08-07 | 10 | 0 | Not Started | Frank | Integration and UAT
7 | Deployment | 6 | Delivery | 2026-08-10 | 2026-08-14 | 5 | 0 | Not Started | Alice | Production rollout

## Settings
Setting | Value
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | true
Visible Columns | id,name,duration,startDate,endDate,progress,status