## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1 | Website Redesign |  | Summary | 2026-05-04 | 2026-08-28 | 85 | 25 | In Progress | PM | Top-level project
1.1 | Research Phase |  | Summary | 2026-05-04 | 2026-05-22 | 15 | 100 | Completed | PM |  |  |  | 1
1.1.1 | Competitor Analysis |  | Research | 2026-05-04 | 2026-05-15 | 10 | 100 | Completed | Alice |  |  |  | 1.1
1.1.2 | User Surveys |  | Research | 2026-05-11 | 2026-05-22 | 10 | 100 | Completed | Bob |  |  |  | 1.1
1.2 | Design Phase | 1.1 | Summary | 2026-05-25 | 2026-06-26 | 25 | 40 | In Progress | PM |  |  |  | 1
1.2.1 | Wireframes | 1.1 | Design | 2026-05-25 | 2026-06-05 | 10 | 100 | Completed | Carol |  |  |  | 1.2
1.2.2 | Visual Design | 1.2.1 | Design | 2026-06-08 | 2026-06-19 | 10 | 30 | In Progress | Carol |  |  |  | 1.2
1.2.3 | Prototype Review | 1.2.2 | Design | 2026-06-22 | 2026-06-26 | 5 | 0 | Not Started | PM |  |  |  | 1.2
1.3 | Development Phase | 1.2 | Summary | 2026-06-29 | 2026-08-14 | 35 | 0 | Not Started | PM |  |  |  | 1
1.3.1 | CMS Setup | 1.2 | Development | 2026-06-29 | 2026-07-10 | 10 | 0 | Not Started | Dave |  |  |  | 1.3
1.3.2 | Page Templates | 1.3.1 | Development | 2026-07-13 | 2026-07-31 | 15 | 0 | Not Started | Eve |  |  |  | 1.3
1.3.3 | Content Migration | 1.3.2 | Development | 2026-08-03 | 2026-08-14 | 10 | 0 | Not Started | Frank |  |  |  | 1.3
1.4 | Launch | 1.3 | Summary | 2026-08-17 | 2026-08-28 | 10 | 0 | Not Started | PM |  |  |  | 1
1.4.1 | QA and Bug Fixes | 1.3 | QA | 2026-08-17 | 2026-08-21 | 5 | 0 | Not Started | Eve |  |  |  | 1.4
1.4.2 | Go Live | 1.4.1 | Delivery | 2026-08-24 | 2026-08-28 | 5 | 0 | Not Started | PM |  |  |  | 1.4

## Settings
Setting | Value
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | true
Visible Columns | id,name,duration,startDate,endDate,progress,status