## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1 | Project Charter Approved |  | Milestone | 2026-05-04 | 2026-05-04 | 0 | 100 | Completed | PM | Milestone | 2026-05-01 | 2026-05-01
2 | Requirements Analysis | 1 | Analysis | 2026-05-05 | 2026-05-16 | 10 | 100 | Completed | Alice |  | 2026-05-05 | 2026-05-16
3 | Requirements Signed Off | 2 | Milestone | 2026-05-19 | 2026-05-19 | 0 | 100 | Completed | PM | Milestone | 2026-05-16 | 2026-05-16
4 | Architecture Design | 3 | Design | 2026-05-19 | 2026-06-06 | 15 | 70 | In Progress | Bob | Slipped 3 days vs baseline | 2026-05-19 | 2026-05-30
5 | Design Review Gate | 4 | Milestone | 2026-06-09 | 2026-06-09 | 0 | 0 | Not Started | PM | Milestone | 2026-06-02 | 2026-06-02
6 | Core Development | 5 | Development | 2026-06-09 | 2026-07-18 | 30 | 0 | Not Started | Carol |  | 2026-06-02 | 2026-07-11
7 | Code Freeze | 6 | Milestone | 2026-07-20 | 2026-07-20 | 0 | 0 | Not Started | PM | Milestone | 2026-07-13 | 2026-07-13
8 | System Testing | 7 | QA | 2026-07-20 | 2026-08-07 | 15 | 0 | Not Started | Dave |  | 2026-07-13 | 2026-07-25
9 | UAT Complete | 8 | Milestone | 2026-08-10 | 2026-08-10 | 0 | 0 | Not Started | PM | Milestone | 2026-07-28 | 2026-07-28
10 | Production Deployment | 9 | Delivery | 2026-08-10 | 2026-08-14 | 5 | 0 | Not Started | Eve |  | 2026-07-28 | 2026-08-01
11 | Project Closure | 10 | Milestone | 2026-08-17 | 2026-08-17 | 0 | 0 | Not Started | PM | Milestone | 2026-08-04 | 2026-08-04

## Settings
Setting | Value
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | true
Visible Columns | id,name,duration,startDate,endDate,progress,status,owner