## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1 | Sprint 12 Planning |  | Ceremony | 2026-05-04 | 2026-05-04 | 1 | 100 | Completed | Scrum Master
2 | User Auth - OAuth2 Flow | 1 | Feature | 2026-05-05 | 2026-05-09 | 5 | 100 | Completed | Alice
3 | User Auth - Session Mgmt | 2 | Feature | 2026-05-12 | 2026-05-14 | 3 | 80 | In Progress | Alice
4 | Dashboard Charts | 1 | Feature | 2026-05-05 | 2026-05-14 | 8 | 60 | In Progress | Bob
5 | API Rate Limiting | 1 | Tech Debt | 2026-05-05 | 2026-05-07 | 3 | 100 | Completed | Carol
6 | Fix: Memory Leak in WS | 1 | Bug | 2026-05-05 | 2026-05-06 | 2 | 100 | Completed | Dave | Hotfix priority
7 | E2E Test Suite Expansion | 2,5 | QA | 2026-05-12 | 2026-05-16 | 5 | 20 | In Progress | Eve
8 | Database Index Optimization | 1 | Tech Debt | 2026-05-05 | 2026-05-09 | 5 | 50 | In Progress | Frank
9 | Code Review and Merge | 3,4,7,8 | QA | 2026-05-19 | 2026-05-20 | 2 | 0 | Not Started | Lead
10 | Sprint 12 Retrospective | 9 | Ceremony | 2026-05-21 | 2026-05-21 | 1 | 0 | Not Started | Scrum Master

## Settings
Setting | Value
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | true
Visible Columns | id,name,category,duration,startDate,endDate,progress,status,owner