## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1 | Requirements Gathering |  |  | 2026-05-04 | 2026-05-08 | 5 | 100 | Completed | Alice
2 | System Design | 1 |  | 2026-05-09 | 2026-05-13 | 5 | 0 | Not Started | Bob
3 | Implementation | 2 |  | 2026-05-14 | 2026-05-23 | 10 | 0 | Not Started | Carol
4 | Testing | 3 |  | 2026-05-24 | 2026-05-28 | 5 | 0 | Not Started | Dave
5 | Deployment | 4 |  | 2026-05-29 | 2026-05-31 | 3 | 0 | Not Started | Eve

## Settings
Setting | Value
Project Name | CPM Linear Chain
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | false
Show Scale Buttons | true
Show Week Labels | false
Show Month Labels | true
Show Day Labels | true
Visible Columns | id,name,dependency,duration,startDate,endDate,progress,status,owner
Category Colors | {}