## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1 | Chain A: Research |  | Research | 2026-06-15 | 2026-06-18 | 4 | 0 | Not Started | Team A | Slack = 2 days (project finishes at day 12)
2 | Chain A: Prototype | 1 | Dev | 2026-06-19 | 2026-06-21 | 3 | 0 | Not Started | Team A
3 | Chain A: Review | 2 | Review | 2026-06-22 | 2026-06-24 | 3 | 0 | Not Started | Team A
4 | Chain B: Vendor Setup |  | Procurement | 2026-06-15 | 2026-06-19 | 5 | 0 | Not Started | Team B | Slack = 4 days
5 | Chain B: Installation | 4 | Infra | 2026-06-20 | 2026-06-22 | 3 | 0 | Not Started | Team B
6 | Chain C: Foundation |  | Build | 2026-06-15 | 2026-06-19 | 5 | 0 | Not Started | Team C | CRITICAL
7 | Chain C: Structure | 6 | Build | 2026-06-20 | 2026-06-23 | 4 | 0 | Not Started | Team C | CRITICAL
8 | Chain C: Finishing | 7 | Build | 2026-06-24 | 2026-06-26 | 3 | 0 | Not Started | Team C | CRITICAL

## Settings
Setting | Value
Project Name | CPM Independent Chains
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | false
Show Scale Buttons | true
Show Week Labels | false
Show Month Labels | true
Show Day Labels | true
Visible Columns | id,name,dependency,duration,startDate,endDate,progress,status,owner
Category Colors | {}