## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
100 | Phase 1: Planning & Design |  | Phase 1 | 2026-05-11 | 2026-05-22 | 12 | 0 | Not Started
101 | Stakeholder Interviews |  | Planning | 2026-05-11 | 2026-05-15 | 5 | 100 | Completed | Alice |  | 2026-05-11 | 2026-05-15 | 100
102 | Architecture Design | 101 | Design | 2026-05-16 | 2026-05-19 | 4 | 0 | Not Started | Bob | CRITICAL -- baseline was 3d, actual is 4d (slipped 1d) | 2026-05-16 | 2026-05-18 | 100
103 | Technical Spec Review | 102 | Review | 2026-05-20 | 2026-05-22 | 3 | 0 | Not Started | Carol | CRITICAL -- started 1d late due to 102 slip | 2026-05-19 | 2026-05-21 | 100
104 | Risk Assessment | 101 | Planning | 2026-05-16 | 2026-05-17 | 2 | 0 | Not Started | Dave | Non-critical -- has 5 days of slack | 2026-05-16 | 2026-05-17 | 100
110 | M1: Planning Complete | 103,104 | Milestone | 2026-05-23 | 2026-05-23 | 0 | 0 | Not Started |  | Gate milestone
200 | Phase 2: Development |  | Phase 2 | 2026-05-23 | 2026-06-05 | 14 | 0 | Not Started
201 | Backend API | 110 | Backend | 2026-05-23 | 2026-05-28 | 6 | 40 | In Progress | Eve | CRITICAL -- baseline started 1d earlier | 2026-05-22 | 2026-05-27 | 200
202 | Frontend UI | 201 | Frontend | 2026-05-29 | 2026-06-02 | 5 | 0 | Not Started | Frank | CRITICAL | 2026-05-28 | 2026-06-01 | 200
203 | End-to-End Testing | 202 | QA | 2026-06-03 | 2026-06-05 | 3 | 0 | Not Started | Grace | CRITICAL | 2026-06-02 | 2026-06-04 | 200
204 | API Documentation | 201 | Docs | 2026-05-29 | 2026-06-01 | 4 | 0 | Not Started | Hank | Non-critical -- has 4 days of slack | 2026-05-28 | 2026-05-31 | 200
210 | M2: Development Complete | 203,204 | Milestone | 2026-06-06 | 2026-06-06 | 0 | 0 | Not Started
300 | Phase 3: Deployment |  | Phase 3 | 2026-06-06 | 2026-06-10 | 5 | 0 | Not Started
301 | Production Setup | 210 | DevOps | 2026-06-06 | 2026-06-08 | 3 | 0 | Not Started | Ivy | CRITICAL | 2026-06-05 | 2026-06-07 | 300
302 | Go-Live & Monitoring | 301 | DevOps | 2026-06-09 | 2026-06-10 | 2 | 0 | Not Started | Jack | CRITICAL | 2026-06-08 | 2026-06-09 | 300
310 | M3: Project Complete | 302 | Milestone | 2026-06-11 | 2026-06-11 | 0 | 0 | Not Started

## Settings
Setting | Value
Project Name | CPM Complex Project
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | false
Show Scale Buttons | true
Show Week Labels | false
Show Month Labels | true
Show Day Labels | true
Visible Columns | id,name,dependency,duration,startDate,endDate,progress,status,owner
Category Colors | {}