## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1 | A1: Initial Setup |  | Setup | 2026-07-01 | 2026-07-03 | 3 | 0 | Not Started | Team A
2 | B1: Infrastructure | 1 | Infra | 2026-07-04 | 2026-07-08 | 5 | 0 | Not Started | Team B | CRITICAL -- longest parallel task after A1
3 | A2: Core Module | 1,2 | Dev | 2026-07-09 | 2026-07-12 | 4 | 0 | Not Started | Team A | CRITICAL -- waits for both A1 and B1
4 | B2: Data Pipeline | 2,3 | Data | 2026-07-13 | 2026-07-15 | 3 | 0 | Not Started | Team B | CRITICAL
5 | A3: UI Polish | 3 | UI | 2026-07-13 | 2026-07-14 | 2 | 0 | Not Started | Team A | Has 1 day of slack
6 | Merge & Deploy | 4,5 | Deploy | 2026-07-16 | 2026-07-16 | 1 | 0 | Not Started | DevOps | CRITICAL

## Settings
Setting | Value
Project Name | CPM Ladder Dependency
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | false
Show Scale Buttons | true
Show Week Labels | false
Show Month Labels | true
Show Day Labels | true
Visible Columns | id,name,dependency,duration,startDate,endDate,progress,status,owner
Category Colors | {}