## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
1 | Project Start |  | Kickoff | 2026-07-13 | 2026-07-13 | 1 | 0 | Not Started | PM
2 | Track A: Server Migration | 1 | Infra | 2026-07-14 | 2026-07-23 | 10 | 0 | Not Started | Alice | CRITICAL -- zero slack
3 | Track B: Database Upgrade | 1 | Database | 2026-07-14 | 2026-07-22 | 9 | 0 | Not Started | Bob | Near-critical -- 1 day slack
4 | Track C: Network Config | 1 | Network | 2026-07-14 | 2026-07-21 | 8 | 0 | Not Started | Carol | 2 days slack
5 | Track D: Security Audit | 1 | Security | 2026-07-14 | 2026-07-20 | 7 | 0 | Not Started | Dave | 3 days slack
6 | Final Verification | 2,3,4,5 | Verification | 2026-07-24 | 2026-07-24 | 1 | 0 | Not Started | PM | CRITICAL -- waits for all tracks

## Settings
Setting | Value
Project Name | CPM Near-Critical Paths
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | false
Show Scale Buttons | true
Show Week Labels | false
Show Month Labels | true
Show Day Labels | true
Visible Columns | id,name,dependency,duration,startDate,endDate,progress,status,owner
Category Colors | {}