## Tasks
Task ID | Task Name | Dependency | Task Category | Start Date | End Date | Duration | Progress (%) | Status | Owner | Remarks | Baseline Start | Baseline End | Parent ID
10 | Phase 1: Discovery |  | Discovery | 2026-04-06 | 2026-04-20 | 15 | 0 | Not Started
11 | Market Research |  | Research | 2026-04-06 | 2026-04-12 | 7 | 100 | Completed | Alice | CRITICAL | 2026-04-06 | 2026-04-12 | 10
12 | User Interviews | 11 | Research | 2026-04-13 | 2026-04-17 | 5 | 100 | Completed | Bob | CRITICAL | 2026-04-13 | 2026-04-17 | 10
13 | Competitive Analysis | 11 | Research | 2026-04-13 | 2026-04-15 | 3 | 0 | Not Started | Carol | Slack = 2 days | 2026-04-13 | 2026-04-14 | 10
14 | Requirements Doc | 12,13 | Planning | 2026-04-18 | 2026-04-20 | 3 | 100 | Completed | Alice | CRITICAL | 2026-04-18 | 2026-04-20 | 10
19 | M1: Discovery Complete | 14 | Milestone | 2026-04-21 | 2026-04-21 | 0 | 100 | Completed
20 | Phase 2: Design |  | Design | 2026-04-21 | 2026-05-05 | 15 | 0 | Not Started
21 | UX Wireframes | 19 | UX | 2026-04-21 | 2026-04-27 | 7 | 60 | In Progress | Diana | CRITICAL -- baseline was 6d, actual 7d | 2026-04-21 | 2026-04-26 | 20
22 | Visual Design | 21 | UI | 2026-04-28 | 2026-05-02 | 5 | 0 | Not Started | Eve | CRITICAL | 2026-04-27 | 2026-05-01 | 20
23 | Design System | 21 | UI | 2026-04-28 | 2026-04-30 | 3 | 0 | Not Started | Frank | Slack = 2 days | 2026-04-27 | 2026-04-29 | 20
24 | Prototype | 22,23 | UX | 2026-05-03 | 2026-05-05 | 3 | 0 | Not Started | Diana | CRITICAL | 2026-05-02 | 2026-05-04 | 20
29 | M2: Design Approved | 24 | Milestone | 2026-05-06 | 2026-05-06 | 0 | 0 | Not Started
30 | Phase 3: Development |  | Development | 2026-05-06 | 2026-05-30 | 25 | 0 | Not Started
31 | Backend API v1 | 29 | Backend | 2026-05-06 | 2026-05-15 | 10 | 0 | Not Started | Grace | CRITICAL | 2026-05-05 | 2026-05-14 | 30
32 | Frontend Shell | 29 | Frontend | 2026-05-06 | 2026-05-12 | 7 | 0 | Not Started | Hank | Slack = 3 days | 2026-05-05 | 2026-05-11 | 30
33 | Auth Module | 31 | Backend | 2026-05-16 | 2026-05-20 | 5 | 0 | Not Started | Grace | CRITICAL | 2026-05-15 | 2026-05-19 | 30
34 | Frontend Pages | 32 | Frontend | 2026-05-13 | 2026-05-20 | 8 | 0 | Not Started | Hank | Non-critical -- joins at integration | 2026-05-12 | 2026-05-19 | 30
35 | Integration | 33,34 | Integration | 2026-05-21 | 2026-05-25 | 5 | 0 | Not Started | Ivan | CRITICAL | 2026-05-20 | 2026-05-24 | 30
36 | Performance Tuning | 35 | DevOps | 2026-05-26 | 2026-05-30 | 5 | 0 | Not Started | Judy | CRITICAL | 2026-05-25 | 2026-05-29 | 30
39 | M3: Code Freeze | 36 | Milestone | 2026-05-31 | 2026-05-31 | 0 | 0 | Not Started
40 | Phase 4: QA & Launch |  | QA | 2026-05-31 | 2026-06-09 | 10 | 0 | Not Started
41 | Regression Testing | 39 | QA | 2026-05-31 | 2026-06-04 | 5 | 0 | Not Started | Karen | CRITICAL | 2026-05-30 | 2026-06-03 | 40
42 | Security Pen Test | 39 | Security | 2026-05-31 | 2026-06-02 | 3 | 0 | Not Started | Leo | Slack = 2 days | 2026-05-30 | 2026-06-01 | 40
43 | Bug Fixes | 41,42 | Dev | 2026-06-05 | 2026-06-07 | 3 | 0 | Not Started | Grace | CRITICAL | 2026-06-04 | 2026-06-06 | 40
44 | Deployment | 43 | DevOps | 2026-06-08 | 2026-06-09 | 2 | 0 | Not Started | Ivan | CRITICAL | 2026-06-07 | 2026-06-08 | 40
49 | M4: Launch! | 44 | Milestone | 2026-06-10 | 2026-06-10 | 0 | 0 | Not Started

## Settings
Setting | Value
Project Name | CPM Long Software Project
Theme Name | Linear Dark
Theme BG Primary | #0f0f12
Theme BG Secondary | #1a1a23
Theme BG Tertiary | #23232f
Theme BG Hover | #2a2a38
Theme Border | #2e2e3a
Theme Border Subtle | #232330
Theme Text Primary | #e8e8ed
Theme Text Secondary | #9898a8
Theme Text Muted | #66667a
Theme Accent | #6366f1
Theme Accent Hover | #818cf8
Theme Success | #22c55e
Theme Warning | #f59e0b
Theme Danger | #ef4444
Theme Info | #3b82f6
Theme Critical Path | #f43f5e
Show Critical Path | true
Show Slack | true
Show Dependencies | true
Show Today Line | true
Show Baseline | true
Skip Weekends | false
Show Scale Buttons | true
Show Week Labels | false
Show Month Labels | true
Show Day Labels | true
Visible Columns | id,name,dependency,duration,startDate,endDate,progress,status,owner
Category Colors | {}